## Sheet1
Risk ID | Risk Category | Risk Description | Root Cause | Triggers / Early Warning Signs | Probability (1–5) | Impact (1–5) | Risk Score (P×I) | Risk Owner | Risk Response Strategy | Mitigation Plan (Before Event) | Contingency Plan (After Event) | Status
R-1 | Resource / Staffing | Only 5 associates available to support 24/7 operations, causing risk of burnout, shift gaps, and service disruption. | Understaffing relative to required 24/7 workload. | Missed shifts, increased absenteeism, overtime spikes, SLA breaches, productivity drop. | 4 | 5 | 20 (High) | Delivery Manager / PM | Mitigate | Hire additional staff/contractors; implement rotating shifts with backups; cross-train team; balance workload; add automation. | Reassign temporary resources; controlled overtime; prioritize critical tasks; engage vendor support. | Open
R-2 | Operational / Process | Manual monitoring of the product dashboard may cause human error, missed alerts, or inaccurate reporting. | Lack of automation and dependency on manual checks. | Delayed issue detection, inconsistent data logs, incorrect reporting, SLA breaches. | 3 | 4 | 12 (Medium-High) | Operations Lead / PM | Mitigate | Automate dashboard alerts; introduce validation checks; implement peer review; train team on monitoring best practices. | Enable emergency incident response; temporarily increase monitoring frequency; revalidate data; escalate to engineering. | Open
R-3 | Knowledge Management / Process | Lack of a KEDB (Known Error Database) leads to delays in incident resolution and repeated troubleshooting of the same issues. | No formal documentation of known errors, fixes, and workarounds. | Increased MTTR, repeated incidents, team asking for same solutions, reliance on tribal knowledge. | 4 | 4 | 16 (High) | Operations Lead / PM | Mitigate | Create and maintain a structured KEDB; document recurring issues and workarounds; enforce update process after every incident. | Engage SMEs to provide quick fixes; accelerate documentation effort; temporarily increase support staffing. | Open
R-4 | Financial / Technical | Splunk Cloud licensing and ingestion costs may be significantly higher compared to the existing Splunk Enterprise (on-prem) setup, increasing operational expenses before full cloud migration is completed. | Partial cloud adoption, unclear volume forecasting, and mismatch between current usage vs. cloud pricing models. | Budget overages, invoice spikes, usage exceeding cloud limits, leadership concerns on ROI. | 3 | 4 | 12 (Medium-High) | PM / Finance Lead / Platform Owner | Mitigate | Conduct cost modeling; review ingestion volumes; optimize log retention; evaluate hybrid model; negotiate pricing tiers with vendor. | Reduce ingestion volume; shift non-critical logs back on-prem; delay full cloud migration; rebaseline budget. | Open
R-5 | Process / Configuration Management | CMDB entries are missing or incomplete due to lack of a standardized process to onboard servers into CMDB during installation, leading to inaccurate asset records and governance issues. | No enforced onboarding process from server build stage; manual CMDB updates; inconsistent ownership. | Missing CI records, audit failures, dependency mapping gaps, change records failing CMDB validation. | 4 | 4 | 16 (High) | CMDB Owner / Infrastructure Manager | Mitigate | Define and implement server-build-to-CMDB workflow; automate CI creation; enforce CMDB checks in deployment pipeline; assign ownership for population/validation. | Perform CMDB reconciliation using discovery tools; run correction project to onboard missing servers; apply temporary manual controls. | Open